	Date
	Invoice #

	4/2/2025
	1002


[image: ]INVOICE
1700 Congress Ave.
Austin, TX 78701
	Bill To:
	
	

	City of Beegeeville
1969 Melody Fair Ave.
Beegeeville, TX 78711
	
	

	
	Project #
	Service Period
	Due Date

	
	CDV25-0016
	2/18/2025-4/1/2025
	8/1/2025

	Milestone
	Description
	Total Contract
	Total Previous 
	% Complete
	Total Current

	1
2
3
4
5
6
7
8
9
	Establishment of Local File
Completion of Fair Housing & Special Condition Requirements
Completion of Environmental Review
Completion of Acquisition Activities Project Financial Management
Completion of Construction Procurement
Labor Standards Compliance & 50%
Completion of Construction
Labor Standards Compliance & 100%
Completion of Construction
Project Completion & Closeout
	


	5,000.00
5,000.00
12,000.00
2,000.00
10,500.00
5,500.00
8,500.00
5,500.00
6,000.00
	
	100%
100% 25% 100% 48%
0%
0%
0%
0%
	  $ 5,000.00
$ 5,000.00
$ 3,000.00
$ 2,000.00
$ 5,000.00

	Total: 
	
	60,000.00
	
	33%
	20,000.00

	Please pay by check or EFT- Chase Bank, Routing 1144000998, Account 593396695
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