| Date | Invoice # |
| --- | --- |
| 4/2/2025 | 1002 |

INVOICE

1700 Congress Ave.

Austin, TX 78701

| Bill To: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| City of Beegeeville 1969 Melody Fair Ave. Beegeeville, TX 78711 |  |  |  |  |  |  |
|  |  | Project # |  | Service Period |  | Due Date |
|  |  | CDV25-0016 |  | 2/18/2025-4/1/2025 |  | 8/1/2025 |
| Milestone | Description | Total Contract |  | Total Previous | % Complete | Total Current |
| 1 2 3 4 5 6 7 8 9 | Establishment of Local File Completion of Fair Housing & Special Condition Requirements Completion of Environmental Review Completion of Acquisition Activities Project Financial Management Completion of Construction Procurement Labor Standards Compliance & 50% Completion of Construction Labor Standards Compliance & 100% Completion of Construction Project Completion & Closeout |  | 5,000.00 5,000.00 12,000.00 2,000.00 10,500.00 5,500.00 8,500.00 5,500.00 6,000.00 |  | 100% 100% 25% 100% 48% 0% 0% 0% 0% | $ 5,000.00 $ 5,000.00 $ 3,000.00 $ 2,000.00 $ 5,000.00 |
| Total: |  |  | 60,000.00 |  | 33% | 20,000.00 |
| Please pay by check or EFT- Chase Bank, Routing 1144000998, Account 593396695 |  |  |  |  |  |  |